## Sheet1
Open Items
Inventory Management System |  |  |  | Last Updated: 12/20/2018
Item No. | Priority | Assigned To | Status | Description
1 | Low | Quentin Terry | Not Started | Create New Customer
2 | Low | Erik W. | Not Started | Create New Product
3 | Low | Kyle Parker | Not Started | Create New Supplier
4 | Medium | Chaitanya C | 25% | NLS - Search Order by product